## Checklist
Category | Checklist item | Owner | Status | Evidence / notes
Requirements | Confirm VpcCidr (172.200.0.0/24) with the client — non-RFC1918 range | Client / HMSG | Not started
Requirements | Confirm ClientVpnCidr 10.200.0.0/22 has no overlap | HMSG | Not started
Requirements | Receive CustomerGatewayIp + OnPremCidr (for the optional S2S VPN) | Client | Not started
Requirements | Receive Entra ID Federation Metadata XML | Client | Not started
Design | Architecture design document approved (Week 1) | Client / HMSG | Not started
Network | Deploy VPC / subnets / route tables / IGW / NAT | HMSG | Not started
Network | Verify flow logs → S3 and lifecycle rules | HMSG | Not started
Security | Security groups allow RDP / MSSQL only from VPN + on-prem ranges | HMSG | Not started
Security | sysadm secret exists in Secrets Manager (NoEcho) | HMSG | Not started
Compute | EC2 launched in db-ec1a (m7i.2xlarge · Win 2022) | HMSG | Not started
Compute | D: 4 TB volume formatted NTFS and mounted | HMSG | Not started
Compute | sysadm local account created and tested | HMSG | Not started
VPN | ACM server certificate issued / imported | HMSG | Not started
VPN | IAM SAML provider updated with real metadata XML | HMSG | Not started
VPN | Client VPN endpoint validated; .ovpn distributed to ≤10 users | HMSG | Not started
VPN | Developer access to the DB host over Client VPN verified | Client / HMSG | Not started
VPN | Site-to-Site VPN created and tunnels UP (if required) | Client / HMSG | Not started
VPN | On-prem route propagated into pri/db route tables verified | HMSG | Not started
Docs | Resource inventory delivered | HMSG | Not started
Docs | Administration guide delivered | HMSG | Not started
Docs | Backup / recovery / VPN configuration delivered | HMSG | Not started
Docs | Completion checklist closed out | HMSG | Not started
Handover | Temporary implementation IAM access removed | HMSG | Not started
Handover | VPN user management transferred to HMGRS | Client / HMGRS | Not started
Handover | Final sign-off obtained | Client / HMSG | Not started

## Legend
Status legend
Done
In progress
Blocked
Not started
Owner: HMSG = implementation team · Client = Hyundai / HMGRS